## Sheet1
Date | Start | End | Breaks | Duration | Activity | Total Time
2020-09-28 | 11:00 | 19:28 | 1:45 | 6:43 | * Got a basic editor window and graph view set up * Set up the basics of file persistance and serialization * Created file importers * Set up git repository and Codacy code analysis * Researched how ShaderGraph handles some of the things I wanted to implement * Set up a Github repository for the project | 53:11
2020-09-29 | 0:00 | 0:00 | 0:00 | 0:00
2020-09-30 | 15:48 | 20:52 | 0:30 | 4:34 | * Added nodes * Added node serialization * Added Undo/Redo (hopefully) and file change tracking * Added search tree for nodes * Researched the internals of ShaderGraph to learn how a bunch of things are done there, then reverse-engineered some of them
2020-10-01 | 11:19 | 19:56 | 0:00 | 8:37 | * Spent a lot of time fixing the Undo/Redo functionality * Spent a bunch more time fixing the Undo/Redo functionality because apparently it's so impossible for my tiny brain to understand that you need to save the Undo state of the object before modifying it, and not afterwards leading to the Undo doing absolutely nothing. :/ * Researched how ShaderGraph implements some features and reversed engineered that into something that works with my architecture (there are quite a few similar things in the codebase but I never just copy pasted things) * Added node connections (edges) and proper serialization and file persistancy for them * Added the ability to drag an edge/connection from a port and drop it somewhere to create a node
2020-10-02 | 10:15 | 11:48 | 0:00 | 1:32 | * Moved graph view into an intermediary visual element that holds everything (toolbar, blackboard etc) * Fixed blackboard visibility issue
2020-10-03 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-04 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-05 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-06 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-07 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-08 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-09 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-10 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-11 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-12 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-13 | 13:26 | 19:35 | 0:00 | 6:10 | * Added Properties (the checks & triggers I was talking about, and Actors which are basically a property that holds which entity owns the dialogue line) * Fixed blackboard: you can now properly delete properties. * Added property (de-)serialization * Added node creation from property (either using the search window provider or by dragging a property from the blackboard) * Did some more research into GraphView and UIElements. * Experimented a bit with writing USS (CSS/UI Styling for UIElements)
2020-10-14 | 11:30 | 18:38 | 3:51 | 3:17 | * Added "Self" dialogue node for when the player has something to say * Implemented a system to have dynamic ports to a node (because it's needed to allow the user to choose character lines * Added custom styling to node * Fixed an issue where the node would get initialized twice when creating a node while dragging a connection from another node
2020-10-15 | 11:22 | 15:58 | 0:00 | 4:36 | * Added NPC node * Added node connection validation * Added styling and custom node layouts (UIElements learning) * Fixed issue where renaming a property would not rename nodes that refer to that property * Started working on copy&paste functionality inside the tool
2020-10-16 | 11:05 | 18:23 | 0:00 | 7:19 | * Finished implementing copy&paste * Added per-node styling and other look/layout related things (UIElements learning) * Fixed an issue where you could connect two ports more than once (i.e. duplicated edges) * Fixed an issue where search window wouldn't be created properly when dragging from port * Fixed an issue where separators between dialogue lines wouldn't get properly removed when removing the corresponding line
2020-10-17 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-18 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-19 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-20 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-21 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-22 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-23 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-24 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-25 | 9:39 | 20:22 | 0:20 | 10:23 | * Added a runtime Dialogue Graph object * Parsed editor data into runtime data (better suited for using in a project) * Fixed an issue where the port capacity was not taken into account (i.e if a port could only accept one connection at a time, the tool would ignore that and default to more than one connection) * Began working on a custom inspector for the runtime monobehaviour * Improved/modified node styling
2020-10-26 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-27 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-28 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-29 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-30 | 0:00 | 0:00 | 0:00 | 0:00
2020-10-31 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-01 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-02 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-03 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-04 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-05 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-06 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-07 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-08 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-09 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-10 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-11 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-12 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-13 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-14 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-15 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-16 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-17 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-18 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-19 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-20 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-21 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-22 | 0:00 | 0:00 | 0:00 | 0:00
2020-11-23 | 0:00 | 0:00 | 0:00 | 0:00